## Slide 1: INOVEXA
Core Platform & EdTech LMS
Project map to first-client go-live, 1 December 2026
Moodle LMS
FastAPI AI
PostgreSQL + Redis
Payments
Django Core
Notes: INOVEXA is a multi-tenant platform: Django is the hub (identity, billing, CRM, tenancy), Moodle and a private FastAPI AI service are spokes. This deck turns the PRD, UML models and the to-do roadmap into one visual story. Source files: PRD, UML, project to-do.

## Slide 2: One goal: first clients live on 1 December 2026
Launch a working multi-tenant EdTech LMS, CRM and AI coaching platform for the first client cohort.
What success looks like
Tenant-aware roles and database isolation in Django
Moodle sign-in and provisioning for a school and an individual
AI coaching end to end, with fair-use controls
Payment to license activation that can be traced
Tenant isolation proven by automated checks
3
apps: Django hub, Moodle, FastAPI
7
gated phases, one active at a time
12
requirements (7 functional, 5 non-functional)
1 Dec
go-live for the first client cohort
Notes: Primary objective from the roadmap: a working multi-tenant EdTech LMS + CRM + AI coaching platform for the first client cohort by 2026-12-01. Phase-gated, with a hard scope boundary.

## Slide 3: Three apps, three jobs
Django: INOVEXA Core
The hub · app.inovexa.com
Identity, organizations and roles
Billing, licenses and payments
Tenant isolation with PostgreSQL RLS
Moodle LMS
Learning spoke · learn.inovexa.com
Courses, quizzes and SCORM
Cohorts and course groups
Signed-token sign-in via a custom plugin
FastAPI AI service
Coaching spoke · private network
Socratic prompts that guide, not answer
Live streaming of feedback (SSE)
Usage ledger and model fallback
Django 5 · Python 3.12 · PostgreSQL 16 (RLS) · Redis 7 + Celery · Moodle 4 · FastAPI · Docker Compose · Nginx + Let's Encrypt
Notes: Hub-and-spoke: Django owns the source of truth for users, billing and tenants. Moodle runs learning. FastAPI runs Socratic AI and is kept off the public internet.

## Slide 4: Architecture: Django is the hub, the others are spokes
Users and clients
Nginx reverse proxy
TLS · domain routing · rate limiting
Payment gateway
mobile money · card
INOVEXA Core · Django
app.inovexa.com
CRM · identity · billing
subscriptions · RLS tenancy
Moodle LMS
learn.inovexa.com
courses · quizzes · SCORM
cohorts · groups · JWT login
FastAPI AI service
internal network only
Socratic prompts · SSE
usage ledger · fallback
Celery workers
provisioning · retries
PostgreSQL 16
inovexa_db · RLS
Redis 7
sessions · queues
PostgreSQL 16
moodle_db
LLM providers
external or self-hosted
no public route
receipt / webhook
grade webhook
quiz context
SSE stream
enqueue
Moodle REST API
provider keys stay in FastAPI env
One VPS · Docker Compose · Nginx is the only public entry point
Notes: Everything public enters via Nginx. FastAPI is on the private Docker network; Moodle or Django call it through authenticated server-to-server channels. Celery workers do Moodle provisioning with exponential-backoff retries. Core tenant data lives in PostgreSQL with row-level security; Moodle has its own database.

## Slide 5: Learner journey: from sign-up to AI feedback
1
USER
Register and pick a plan
Individual or school signs up.
2
USER
Pay
Mobile money or card.
3
DJANGO
Payment receipt
Webhook activates the license.
4
CELERY
Create Moodle user
Moodle REST API, async task.
5
CELERY
Cohort or group
School: cohort. Individual: group.
6
DJANGO
Signed SSO token
JWT: identity, cohort, expiry.
7
MOODLE
Validate and log in
Custom auth plugin starts session.
8
MOODLE
Attempt a quiz
Stuck answers go to the AI.
9
FASTAPI
Socratic evaluation
Guides step by step, no answer.
10
FASTAPI
Stream feedback
SSE into the quiz, under 1.5 s.
11
MOODLE
Quiz complete
Completion or grade event.
12
DJANGO
Grade webhook
Django records the sync.
Failure path: webhook or Moodle API errors retry with exponential backoff. Retry limits, duplicate events and dead-letter handling are still open.
Notes: Twelve steps across four systems. Step 5 branches: institutional organizations get a Moodle cohort and members; individuals are enrolled into a standard course group. Targets: provisioning under 3 seconds after payment (FR-02) and first AI token under 1.5 seconds (FR-03). Retries come from NFR-03.

## Slide 6: Socratic AI: guided hints under a fair-use budget
Moodle quiz
question · rubric · answer
Build the prompt
context + mastery + Socratic rule
High-tier quota reached?
High-tier model
default path
Lighter model
Llama-3 / Qwen class
Stream (SSE)
first token < 1.5 s
No
Yes
Only non-critical interactions are downgraded, so the service stays up.
500
Socratic interactions a month on the standard student plan
Pooled
Schools share one allowance sized by active student seats
Ledger
Reserve, consume and reconcile every interaction, in tokens too
Still open: whether the allowance is checked before or after model choice, how an interaction maps to tokens, and what counts as "critical".
Notes: Moodle sends the question stem, rubric, the student working and a mastery score. FastAPI assembles a prompt with the directive to guide step by step and never give the final answer, applies allowance and model policy, and streams feedback back over SSE. Provider API keys live only in FastAPI environment variables. Interaction is the customer-facing unit; tokens are the internal cost unit; the ledger reconciles both.

## Slide 7: Every client is an organization, isolated by the database
ORGANIZATION
id (uuid, PK)
name
org_type: individual, school, sme, ngo, enterprise
status: pending, active, suspended
created_at
USER_PROFILE
id (uuid, PK)
user_id → auth_user
organization_id → organization
role: org_admin, teacher, student, parent, sme_staff
phone_number
SUBSCRIPTION_LICENSE
id (uuid, PK)
organization_id → organization
product_code: EDTECH_LMS, CRM_BASIC, AI_PRO
seat_capacity · moodle_cohort_id
AI token allowance and usage · valid_until
1 → N
1 → N
How a request stays inside its own tenant (PostgreSQL row-level security)
1 Request
User profile supplies organization_id
2 Middleware
SET LOCAL app.current_organization_id
3 RLS policy
Rows visible only where organization_id matches
4 Teardown
Connection reset, no cross-tenant leakage
Fail closed: Missing tenant context means no access.
Celery tasks: Resolve tenant context explicitly.
Defence in depth: RLS in the database plus Django checks.
Notes: The polymorphic schema means individuals, schools, SMEs, NGOs and enterprises are all just Organizations. Tenant context is derived per request, injected with SET LOCAL, enforced by RLS policies with FORCE ROW LEVEL SECURITY, and reset at teardown. The PRD does not say whether one auth user can belong to several organizations.

## Slide 8: Lifecycles: organization, license and payment are separate
Pending
Active
Suspended
Expired
Cancelled
enrollment approved
verification blocked
policy / admin action
reinstated
subscription expired
renewal completed
cancellation
terminated
Organization.status. Dashed states are target-state additions, not in the original PRD.
SubscriptionLicense
active · expired · suspended · cancelled
valid_until stays a data field, not the whole lifecycle.
Payment
pending → succeeded · failed · cancelled
Tracked with an event log for retries and webhooks.
Notes: Three separate state machines. The PRD defines pending, active and suspended for Organization. The target-state decisions add expired and cancelled, and keep license and payment status separate from organization status.

## Slide 9: Roadmap: seven gated phases in 50 days
13 Oct
20 Oct
27 Oct
3 Nov
10 Nov
17 Nov
24 Nov
1 Dec
Phase 0 Setup & guardrails
13–18 Oct
Phase 1 Core & contracts
19–27 Oct
Phase 2 Tenancy & billing
28 Oct–5 Nov
Phase 3 Moodle & SSO
6–14 Nov
Phase 4 AI & fair use
15–22 Nov
Phase 5 Payments & E2E
23–28 Nov
Phase 6 Pilot launch
3 days
Today, 14 Oct
Go-live 1 Dec
Tightest windows: Phase 3 (9 days), Phase 4 (8 days) and Phase 6 (3 days).
Notes: Timeline from the roadmap: Phase 0 13-18 Oct; Phase 1 19-27 Oct; Phase 2 28 Oct-5 Nov; Phase 3 6-14 Nov; Phase 4 15-22 Nov; Phase 5 23-28 Nov; Phase 6 29 Nov-1 Dec. Only one phase is active at a time and each closes with a gate.

## Slide 10: What each phase delivers
Phase | Dates | What gets built | Exit gate
Phase 0 | 13–18 Oct | Charter, repo and Docker baseline, AI guardrails, decision log | Scope signed off; PRD and UML locked as source of truth
Phase 1 | 19–27 Oct | Core schema, RLS baseline, Django bootstrap, API contract | Boots locally; tenant isolation tests pass
Phase 2 | 28 Oct–5 Nov | Roles, license and payment states, individual and school onboarding | One valid subscription path; RBAC boundaries enforced
Phase 3 | 6–14 Nov | Moodle user and cohort tasks with retries, JWT sign-in, auth plugin | Both onboarding paths provision; signed SSO login works
Phase 4 | 15–22 Nov | Socratic endpoint, SSE streaming, usage ledger, downgrade rules | First-token latency met; fair use and fallback verified
Phase 5 | 23–28 Nov | Payment activation, webhook checks, monitoring, restore runbook | End-to-end paths proven; launch checklist complete
Phase 6 | 29 Nov–1 Dec | Pilot data, controlled launch, change freeze, go/no-go | First client live; release baseline frozen
Notes: Each phase has a milestone, activities with tasks, deliverables and evidence, and exit criteria. A phase closes only when every task has passed verification and the gate record is signed.

## Slide 11: Scope stays narrow, and every phase closes at a gate
In scope until go-live
Django core with tenant-aware roles and RLS
Individual and school onboarding
Payment to license activation
Moodle provisioning and JWT sign-in
Socratic AI with fair-use controls
Monitoring, restore plan, launch checklist
Out of scope until after go-live
SME and NGO CRM expansion
Enterprise project-management modules
Broad CRM redesign or extra AI features
Multi-region deployment
Refactors unrelated to the active phase
Anything without a PRD requirement ID
Every phase closes the same way
Tasks done, with evidence
Exit criteria checked
Gate record: risks, unknowns, scope
Go or no-go for next phase
Notes: Hard scope rules: only tasks in the current phase are active; no Phase II features; no speculative architecture; every task maps to a PRD requirement or UML diagram. The phase gate template records tasks with evidence, remaining risks, unknowns, scope check and a go/no-go.

## Slide 12: Ten rules keep AI-assisted coding on scope
1
Requirement-first
Every output traces to a PRD or UML item
2
Phase-lock
Only the current phase and task
3
One issue per task
One crisp acceptance criterion each
4
No speculation
No frameworks built "just in case"
5
Evidence first
Tests or validation output before merge
6
Security first
No public FastAPI, tenant or webhook bypass
7
No scope creep
Drifting? Stop and reframe the task
8
Decision log
Record anything the PRD does not state
9
Minimal output
Narrow and exact, no boilerplate
10
Exit gate
Phase closes only when every task is verified
Notes: These are the mandatory grounding guardrails from the to-do file. Any AI-generated code must be tagged to the requirement ID, architecture component, phase and task it satisfies.

## Slide 13: Coverage: 9 of 12 requirements have explicit tasks
Chart: 
| Explicit tasks | Partly covered | No task
Requirements | 9 | 2 | 1
Mapped from the to-do list against FR-01 to FR-07 and NFR-01 to NFR-05. Please confirm against your own tracker.
PARTLY COVERED
FR-01
Bulk CSV enrollment has no task
Add it to the Phase 2.3 acceptance criteria.
PARTLY COVERED
FR-04
Moodle-side roles have no task
Add role mapping to the Phase 3 contract.
NO TASK
NFR-02
500 concurrent quiz takers is untested
Add a load test to Phase 5; today only isolation under concurrency is tested.
Notes: Nine requirements map cleanly to named tasks (FR-02, FR-03, FR-05, FR-06, FR-07, NFR-01, NFR-03, NFR-04, NFR-05). FR-01 lacks an explicit bulk-CSV task; FR-04 lacks Moodle-side role mapping; NFR-02 (500 concurrent quiz takers) has no load-test task.

## Slide 14: Six risks to watch before go-live
Compressed schedule
Phase 3 gets 9 days, Phase 4 gets 8 and Phase 6 only 3. Little slack if a gate fails.
500 users untested
NFR-02 has no load test, and one VPS alone does not prove capacity.
Payment provider open
Phase 2 uses a mock gateway. Pick the real mobile-money or card provider early.
Latency targets
Define where the 3 s and 1.5 s clocks start and stop, and which percentile counts.
Webhook details open
Retry limits, dead-letter queue, JWT claims, key rotation and Moodle-to-AI auth.
Operations basics
VPS sizing, backup frequency, alert thresholds and secrets rotation are not set.
Notes: These are observations from reading the PRD, UML and to-do together. Red icons are the two that threaten the date or the capacity claim; amber icons are definitions and decisions that should be settled early; grey is operational basics due by Phase 5.3.

## Slide 15: This week: close Phase 0 (13–18 Oct)
Governance
Sign off the project charter
Define the phase gates
Lock PRD and UML as source of truth
Baseline
Repo structure and branch strategy
Docker Compose skeleton for all five services
Architecture baseline with trust boundaries
Guardrails
AI usage rules and phase lock
Task-to-requirement traceability template
Review and quality gates
Suggested early decisions
Choose the payment provider · Fix the latency measuring points · Map system_admin and org_admin permissions
Notes: Phase 0 tasks come straight from the roadmap: governance (charter, phase gates, source-of-truth list), implementation baseline (repo, environment, architecture diagram) and guardrails (AI rules, traceability template, review gates). The three decisions are suggestions drawn from the open items in the UML document.

## Slide 16: One controlled release, not a platform expansion
One phase at a time
Every task traces to a requirement
Evidence before every gate
Go-live: 1 December 2026
Notes: Closing recommendation from the roadmap: do not parallelize broad workstreams; keep the team on one active phase and enforce the gate. The first client release is a controlled delivery event.